## Instructions
Risk Register Instructions
A risk register for all types of projects is provided in the Risk Register worksheet. The risk register is organized with the following columns:
Risk Statement: a clear and concise explanation of the context of the risk. The risk statement includes the:
Risk (Event) Description: explanation of the risk event or the occurrence that has caused the risk (e.g., customer submits changes to requirements after requirements are baselined)
Risk Consequence: potential effect or outcome of the risk (e.g., changes could extend project delivery completion date)
Risk Trigger/Causes: act or event that serves as a stimulus and initiates or precipitates the risk
Assessment: a value (e.g., Low=1, Medium=2, High=3) that represents the result of identifying, classifying, analyzing, and prioritizing risk
Impact: result of determining the nature of possible effects of the risk
Probability: degree of likelihood or chance that the risk will occur
Total: sum of the Impact, Probability, and Level of Control values; the cell contains a formula that will calculate the sum automatically
Risk Response Strategy: one or more options to address the risk
Actions Required to Implement Response Strategy: activities that will be carried out in order to accomplish the risk response strategy (e.g., revising the Project Plan to include additional activities, defining various alternatives to address the risk)
Risk Owner: name of the individual(s) or party(s) responsible for managing the risk
Completion Date: date mm/dd/yy the risk response actions were completed

## Risk Register
Risk Register
Risk Register
Agency/Organization Name: Study GRC, Inc. | [8 empty] | Version Number | 1
Project Name: ORG WIDE | [8 empty] | Revision Date mm/dd/yy
| RISK STATEMENT |  |  | ASSESSMENT (Scale of 1-10)
Risk # | Risk (Event) Description | Impact (Consequence) Description | Risk Trigger / Causes | Impact | Likelihood | Total | Risk Response Strategy | Actions Required To Implement Response Strategy | Risk Owner | Completion Date mm/dd/yy
1 | Phishing Email - File Download | Malware infection, data loss, ransomware, operational disruption. | End-user clicking phishing link, social engineering. | 8 | 2 | 16 | Antivirus Software, Firewall, Security Awareness Training | Implement annual security awareness training Phishing email awareness training quarterly Regularly ensuring updated antivirus | Evan, CISO | --
2 | Data Deletion or Removal - File System | Loss of business-critical data, operational disruption, recovery costs. | End-user error, malicious actor, software malfunction. | 6 | 3 | 18 | Regular backups, BCP DRP, version control, access control, MFA | Proper policy management, implment backups schdules, enforce version control and MFA. | CTO / CISO
3 | Lack of Disaster Recovery | Extended operational downtime, data loss, financial loss, reputational damage. | Powerloss, Data loss, Inability due to physical event, lack of proactive approach. | 5 | 6 | 30 | Proper policy management, contact list org-chart. | Implement playbooks for recovery, BIA | CISO | `
4 | Automation Process Failures | Lack of event promotion, outdated community calendar, potential impact on brand reputation. | Platform failure, lack of failover, DDoS attack, misconfigured automations. | 2 | 7 | 14 | Separation of duties and verification through-out process. | Line out a separate person who would review and enable automations. | CTO
5 | Account Takeover - Compromise | Brand reputation damage, data loss/exfiltration, financial loss, legal issues, operational disruption. | Weak passwords, phishing, malware, credential stuffing, lack of MFA. | 8 | 3 | 24 | MFA, Awareness Training, Antivirus, Strong Passwords | Enforce MFA and strong passwords, obtain and deploy antivirus, regular awareness training program. | CISO
6 | Legal Issues or Fines | Financial penalties, reputational damage, legal costs, operational disruption. | Non-compliance with regulations (e.g., GDPR, CCPA), contractual breaches. | 8 | 2 | 16 | Education/Training, Insurance, Consult. | Regular training to ensure compliance, seek legal consults, review insurance options. | President CISO CFO
7 | Account Lockout / Loss | Business operational disruption, data inaccessibility, productivity loss. | Incorrect password attempts, system errors, malicious activity. | 8 | 2 | 16 | Alias emails, IR plan for accounts, backup recovery options. | Develop IR plan for account(s) recovery process, implement and regularly confirm account back options, implement alias emails. | CISO
8 | Insider Threat | Data loss/exfiltration, financial loss, operational disruption, reputational damage. | Malicious intent, negligence, disgruntled employee. | 5 | 1 | 5 | Proper access controls, "need to know basis", regular review. | Implement least privilege, regular log reviews. | CISO
9 | Misconfiguration of Access Controls | Data loss/exfiltration, reputational damage, operational disruption. | Human error, system vulnerability, lack of change management. | 8 | 3 | 24 | Regular review, restrict access/use, separation of duties. | Monthly access control reviews, where possible prevent usage of super user accounts, separation of duties and review. | CTO / CISO
10 | Lack of Regulatory Compliance | Fines, reputational damage, financial loss, operational disruption. | Failure to implement required controls, changes in regulations, not being informed. | 8 | 5 | 40 | Align policy with regulations, education/training | Policy implementation and regular, on-going, training/education to ensure compliance. Bi-annual reviews for compliance.
11 | Fraudulent Business Dealings | Financial loss, reputational damage, legal issues. | Misrepresentation, bribery, corruption. | 8 | 3 | 24 | Separation of duties, review and documentation. | Ensure somebody else issues payment, review, enforce meeting transcripts, email log review. | CTO / CISO
12 | Loss of Key Personnel | Disruption of operations, loss of expertise, difficulty in maintaining momentum. | Resignation, illness, retirement. | 6 | 3 | 18 | Document workflows, cross-training, sharing updates and status. | Implement cross-training requirements and enforce policy for regular updates. | CISO
13 | Platform Dependency | Loss of community engagement, disruption of operations, difficulty in transitioning to a new platform. | Platform downtime, policy changes, acquisition by another company. | 6 | 4 | 24 | Plan for downtime with backup options, keep a list of similar platforms. | Research and implement backup options for critical impact items, develop and keep an updated list of platform backups to use in such event. | President / CISO
14 | Content Quality Issues | Loss of credibility, decreased community trust, negative brand perception. | Inaccurate information, outdated content, poor presentation. | 6 | 2 | 12 | Peer review, quality assurance during lives, brand kit policy. | Implement peer review for material prior, live quality assurance, branding/material policies and guide. | President
15 | Lack of Community Moderation | Toxic behavior, spam, disruptive activities, damaged community environment. | Insufficient moderation resources, lack of clear guidelines, ineffective moderation tools. | 4 | 2 | 8 | Test and Improve Automod, Make channel purposes clear, Increase mods. | Further refine automod, continuely enforce channel purposes, increase mods for increased presence and respond. | CISO
16 | Dependence on External Partners | Disruption of operations, loss of resources, difficulty in meeting community needs, brand perception/reputational damage. | Partner's financial difficulties, changes in strategy, termination of partnership. | 6 | 3 | 18 | Venting Process, Regular Partner Review, Budgetting | Implement partner validation, reliability, and culture fit process. Quarterly partner review. Limiting dependence on partners, proper budgetting. | CFO President
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
Risk Statement: a clear and concise explanation of the context of the risk. The risk statement includes the:
Risk (Event) Description: explanation of the risk event or the occurrence that has caused the risk (e.g., customer submits changes to requirements after requirements are baselined)
Risk Consequence: potential effect or outcome of the risk (e.g., changes could extend project delivery completion date)
Risk Trigger/Causes: act or event that serves as a stimulus and initiates or precipitates the risk
Assessment: a value (e.g., Low=1, Medium=2, High=3) that represents the result of identifying, classifying, analyzing, and prioritizing risk
Impact: result of determining the nature of possible effects of the risk
Probability: degree of likelihood or chance that the risk will occur
Total: sum of the Impact, Probability, and Level of Control values; the cell contains a formula that will calculate the sum automatically
Risk Response Strategy: one or more options to address the risk
Actions Required to Implement Response Strategy: activities that will be carried out in order to accomplish the risk response strategy (e.g., revising the Project Plan to include additional activities, defining various alternatives to address the risk)
Risk Owner: name of the individual(s) or party(s) responsible for managing the risk
Completion Date: date mm/dd/yy the risk response actions were completed

## Likeihood & Risk Values
Likeihood and Impact Values in accordance with NIST SP 800-30r1
https://doi.org/10.6028/NIST.SP.800-30r1
Likelihood of Threat Event Initiation (Adversarial) |  |  | Risk Values
Quantitative Value | Description |  | Calculates quantifiable risk on likelihood and impact.
10 | Adversary is almost certain to initiate the threat event. |  | Impact --> | 0 | 2 | 5 | 8 | 10
8 | Adversary is highly likely to initiate the threat event. | Likelihood | 10 | 0 | 20 | 50 | 80 | 100
5 | Adversary is somewhat likely to initiate the threat event. |  | 8 | 0 | 16 | 40 | 64 | 80
2 | Adversary is unlikely to initiate the threat event. |  | 5 | 0 | 10 | 25 | 40 | 50
0 | Adversary is highly unlikely to initiate the threat event. |  | 2 | 0 | 4 | 10 | 16 | 20
|  |  | 0 | 0 | 0 | 0 | 0 | 0
Likelihood of Threat Event Initiation (Non-Adversarial)
Quantitative Value | Description |  | Impact --> | 0 | 2 | 5 | 8 | 10
10 | Error, accident, or act of nature is almost certain to occur; or occurs more than 100 times a year. | Likelihood | 10 | 0 | 1 | 2.5 | 4 | 5
8 | Error, accident, or act of nature is highly likely to occur; or occurs between 10-100 times a year. |  | 8 | 0 | 0.8 | 2 | 3.2 | 4
5 | Error, accident, or act of nature is somewhat likely to occur; or occurs between 1-10 times a year. |  | 5 | 0 | 0.5 | 1.25 | 2 | 2.5
2 | Error, accident, or act of nature is unlikely to occur; or occurs less than once a year, but more than once every 10 years. |  | 2 | 0 | 0.2 | 0.5 | 0.8 | 1
0 | Error, accident, or act of nature is highly unlikely to occur; or occurs less than once every 10 years. |  | 0 | 0 | 0 | 0 | 0 | 0
Old school Risk Value Translated (value / 20)
Impact of Threat Events |  |  | Legend: | Low | Moderate |  | High
Quantitative Value | Description
10 | The threat event could be expected to have multiple severe or catastrophic adverse effects on organizational operations, organizational assets, individuals, other organizations, or the Nation.
8 | The threat event could be expected to have a severe or catastrophic adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation. A severe or catastrophic adverse effect means that, for example, the threat event might: (i) cause a severe degradation in or loss of mission capability to an extent and duration that the organization is not able to perform one or more of its primary functions; (ii) result in major damage to organizational assets; (iii) result in major financial loss; or (iv) result in severe or catastrophic harm to individuals involving loss of life or serious life-threatening injuries.
5 | The threat event could be expected to have a serious adverse effect on organizational operations, organizational assets, individuals other organizations, or the Nation. A serious adverse effect means that, for example, the threat event might: (i) cause a significant degradation in mission capability to an extent and duration that the organization is able to perform its primary functions, but the effectiveness of the functions is significantly reduced; (ii) result in significant damage to organizational assets; (iii) result in significant financial loss; or (iv) result in significant harm to individuals that does not involve loss of life or serious life-threatening injuries.
2 | The threat event could be expected to have a limited adverse effect on organizational operations, organizational assets, individuals other organizations, or the Nation. A limited adverse effect means that, for example, the threat event might: (i) cause a degradation in mission capability to an extent and duration that the organization is able to perform its primary functions, but the effectiveness of the functions is noticeably reduced; (ii) result in minor damage to organizational assets; (iii) result in minor financial loss; or (iv) result in minor harm to individuals.
0 | The threat event could be expected to have a negligible adverse effect on organizational operations, organizational assets, individuals other organizations, or the Nation.